## Sheet1
Team | Name | Squad/Project | JIRA / TFS Ticket | JIRA Desc | PI | Sprint/Function | Release Cycle | Story Point Planned | Story Point Completed | Assigned On | Sprint Start Date | Sprint End Date | Estimated Date by Developer | % Completion | If Reopned by QA | Status | Internal Status | Current-Last Sprint | Comments | Original Sprint
WPV | Pushkar |  | AFA-11203 | New Client Onboarding - PMDX Manager UI - Develop Client Onboarding Tab | PI#5 | 4 |  | 13 | 13 | 2020-09-22 | 2020-09-24 | 2020-10-07 | 2020-10-07 | 90% |  | On Hold | On Hold |  | New Client Onboarding - PMDX Manager UI - Develop Client Onboarding Tab | PI#5-4 -- NEW
WPV | Pushkar |  | AFA-11266 | Develop Portfolio Configuration Code | PI#5 | 5 |  | 13 | 13 | 2020-10-07 | 2020-10-08 | 2020-10-21 | 2020-10-21 | 100% |  | Closed | Completed |  | Portfolio Config code is completed and PR is merged to develop. | PI#5-5 -- NEW
WPV | Pushkar |  | AFA-11267 | JUNIT for Portfolio Config | PI#5 | 5 |  | 5 | 5 | 2020-10-07 | 2020-10-08 | 2020-10-21 | 2020-10-21 | 100% |  | Closed | Completed |  | Portfolio Config JUnits are completed and PR is merged to develop. | PI#5-5 -- NEW
WPV | Pushkar |  | AFA-11224 | Develop Hub Configuration Code + JUNIT | PI#5 | 6 |  | 8 | 8 | 2020-10-30 | 2020-10-22 | 2020-11-04 | 2020-11-04 | 100% |  | Closed | Completed |  | Hub Config code is completed and PR is merged to develop. | PI#5-6 -- NEW
WPV | Pushkar |  | AFA-11344 | New Client Onboarding - PMDX Manager Server - JUnits and addressing review comments for Hub Config Implementation | PI#5 | 6 |  | 8 | 8 | 2020-10-30 | 2020-10-22 | 2020-11-04 | 2020-11-04 | 100% |  | Closed | Completed |  | New Client Onboarding - PMDX Manager Server - JUnits and addressing review comments for Hub Config Implementation | PI#5-6 -- NEW
WPV | Pushkar |  | AFA-11433 | New Client Onboarding - PMDX Manager PR merge to develop post addressing review comments | PI#6 | 0 |  | 8 | 8 | 2020-11-03 | 2020-11-05 | 2020-11-18 | 2020-11-17 | 100% |  | Closed | Completed |  | New Client Onboarding - PMDX Manager PR merge to develop post addressing review comments | PI#6-0 -- NEW
WPV | Pushkar |  | AFA-11434 | New Client Onboarding - PMDX Manager Externalization of PrivateMarketsDXManager.properties file | PI#6 | 0 |  | 5 | 0 | 2020-11-03 | 2020-11-05 | 2020-11-18 | 2020-11-17 | 90% |  | On Hold | On Hold |  | New Client Onboarding - PMDX Manager Externalization of PrivateMarketsDXManager.properties file | PI#6-0 -- NEW
WPV | Pushkar |  | AFA-11595 | Local setup for aCRM workstream [understand existing user account mapping] | PI#6 | 1 |  | 5 | 5 | 2020-11-02 | 2020-11-19 | 2020-12-02 | 2020-12-02 | 100% |  | Closed | Completed |  | 1. Prerequisite : To make Transformer and CRM Transformer up and running. | PI#6-1 -- NEW
|  |  |  | Tasks | [14 empty] | 2. Reached out to Rahul Verma with my X Drive mapped along-with PrivateMarketsDxTransformer up and running.
|  |  |  | - CRM Setup [Rahul Verma will provide more information] | [14 empty] | 3. Worked with Rahul Verma Setting up code for aCRM.
4. Worked on Second part of US to understand existing User Accounts Mappings of BLK Clients.
5. This will be used for designing User Account Mapping Skeleton.
WPV | Pushkar |  | AFA-11596 | Develop Service in CRM Loader for calling Aladdin ListUsers API fetching list of all users | PI#6 | 2 |  | 8 | 8 | 2020-11-02 | 2020-12-03 | 2020-12-16 | 2020-12-16 | 100% |  | Closed | Completed |  | Develop Service in CRM Loader for calling Aladdin ListUsers API fetching list of all users | PI#6-1 -- NEW
WPV | Jiban |  | AFA-11666 | Bank Account plugin - Skeleton plugin within transformer | PI#6 | 2 |  | 2 | 2 | 2020-11-26 | 2020-12-03 | 2020-12-16 | 2020-12-07 | 100% |  | Closed | Completed |  | Bank Account plugin - Skeleton plugin within transformer | PI#6-2 -- NEW
|  |  |  | - Shared wiki link, standard format | [14 empty] | - Shared wiki link, standard format
|  |  |  | Pending | [14 empty] | Pending
|  |  |  | - Dependency | [14 empty] | - Dependency
|  |  |  | - Code merge | [14 empty] | - Code merge
|  |  |  | Completed | [14 empty] | Completed
|  |  |  | - PR Raised - Approved | [14 empty] | - PR Raised - Approved
|  |  |  | - Package/structure - skeleton completed | [14 empty] | - Package/structure - skeleton completed
WPV | Shahul |  | AFA-11399 | Add field fund status in portfolio | PI#6 | 1 |  | 3 | 3 | 2020-11-19 | 2020-11-19 | 2020-12-02 | 2020-12-02 | 100% |  | Closed | Completed |  | PR is merged with develop branch. | PI#6-1 -- NEW
|  |  |  | - Update Schema(2)-Json | [14 empty] | PR rasied - Monday 7th
- Update Decoder
The end to end testing is not done. it will be done in a seperate Jira.
WPV | Vivek |  | AFA-11597 | Create Bank Account proto file (available) | PI#6 | 2 |  | 8 | 8 | 2020-11-26 | 2020-12-03 | 2020-12-16 | 2020-12-07 | 100% |  | Closed | Completed |  | Updated and committed the changes into the Azure PR need to be raised once got the confirmation will raise the PR. | PI#6-2 -- NEW
- check on what level task
|  |  |  | - PR Raised | [14 empty] | Need to update the existing proto file with the given details and validate the numbers and Need to discuss with Anil about the Asset Entity whether have to use the existing one or need to add new message for Asset Entity.
Blocker : build fail issue.
Help : Prashant helping to resolve build issue (Space issue)
WPV | Vivek |  | AFA-11646 | Bank Account Writer: POC for validating value30 column persistence via SSI creation API | PI#6 | 2 |  | 5 | 5 | 2020-12-09 | 2020-12-03 | 2020-12-16 | 2020-12-14 | 100% |  | Closed | Completed |  | Pass delivery method and test | PI#6-2 -- NEW
Got the clarification from Prashant today I need to start the validation.
WPV | Jiban |  | AFA-11695 | Fund /SPV - Related to Validation and enrichment(Sub task#JIRA 11370 SP: 13) | PI#6 | 3 |  | 8 | 8 | 2020-12-16 | 2020-12-17 | 2020-12-30 | 2020-12-30 | 100% |  | Closed | Completed |  | Need more clarification from Prashant [ Configuration done] | PI#6-3 -- NEW
|  |  |  | Configuration Tasks - ETA 10-Dec | [14 empty] | Dependency : Field mapping not considered as a part of this US will be considered in future.
|  |  |  | - Modify Enum classes - Completed | [14 empty] | Way forwad : Break this story - What can be done and what can not be done. Working on writing JUnits Test Case. Testcases checked in. PR will be raised once Prashant gives confirmation.
|  |  |  | - Create 2 Json file - Completed[field mapping WIP] | [14 empty] | PR Raised. Merged to develop branch
- Schema validation - Completed
Implementation tasks
- Validation on managed/SPV - In progress
- Working on extract part
- JUnit [WIP] (Test Case Skeleton is ready)
WPV | Pushkar |  | AFA-11673 | Move Service in CRM Loader for calling Aladdin ListUsers API for fetching list of all Users to privatemarkets-common library | PI#6 | 3 |  | 3 | 3 | 2020-12-16 | 2020-12-17 | 2020-12-30 | 2020-12-30 | 100% |  | Closed | Completed |  | Need to move service defined in CRMLoader to privatemarkets-common library so it can be leveraged by other applications. Need to refactor JUnits and Source Code if required. | PI#6-3 -- NEW
Working on PR review comments fix.
WPV | Shahul |  | AFA-11399 | Add field fund status in portfolio | PI#6 | 2 |  | 3 | 3 | 2020-11-19 | 2020-12-03 | 2020-12-16 | 2020-12-07 | 100% |  | Closed | Completed |  | PR is merged with develop branch. | PI#6-1 -- SPILL
|  |  |  | - Update Schema(2)-Json | [14 empty] | PR rasied - Monday 7th
- Update Decoder
The end to end testing is not done. it will be done in a seperate Jira.
WPV | Shahul |  | AFA-11465 | Create Shell Share class - Managed fund /SPV | PI#6 | 2 |  | 8 | 8 | 2020-11-26 | 2020-12-03 | 2020-12-16 | 2020-12-16 | 100% |  | Closed | Completed |  | working on top of changes done by Aishwarya. Will raise PR on 29 Dec 2020. | PI#6-2 -- NEW
|  |  |  | - Add new attribute in asset proto | [14 empty] | PR to be raised on 6 Jan. Need to move this story to Sprint 4. Environment dependency. Build was getting failed on 11 Jan.
- Call asset loader from portfolio transformer
- development
- Junit
- Cucumber testing [Need more information]
WPV | Shahul |  | AFA-11465 | Create Shell Share class - Managed fund /SPV | PI#6 | 3 |  | 8 | 8 | 2020-11-26 | 2020-12-17 | 2020-12-30 | 2020-12-30 | 100% |  | Closed | Completed |  | working on top of changes done by Aishwarya. Will raise PR on 29 Dec 2020. | PI#6-2 -- SPILL
|  |  |  | - Add new attribute in asset proto | [14 empty] | PR to be raised on 6 Jan. Need to move this story to Sprint 4. Environment dependency. Build was getting failed on 11 Jan.
- Call asset loader from portfolio transformer
- development
- Junit
- Cucumber testing [Need more information]
WPV | Shahul |  | AFA-11384 | Create FUND/PRIVATE Securities for Managed Funds and Managed Funds SPVs | PI#6 | 3 |  | 5 | 5 | 2020-12-16 | 2020-12-17 | 2020-12-30 | 2020-12-30 | 100% |  | Closed | Completed |  | working on top of changes done by Aishwarya. Will raise PR on 29 Dec 2020. | PI#6-3 -- NEW
PR to be raised by 30th Dec. Need to move this story to Sprint 4. Environment dependency. Build was getting failed on 11 Jan.
WPV | Jiban |  | AFA-11749 | Bank Account integration testing | PI#6 | 3 |  | 8 | 0 | 2020-12-22 | 2020-12-31 | 2021-01-13 | 2021-01-07 | 65% |  | Development | In Progress |  | 60% of development was completed #3, | PI#6-3 -- NEW
|  |  |  | 1. Feature file is completed | [14 empty] | Moved to Sprint#4
|  |  |  | 2. Runner is completed | [14 empty] | 'This was assigned in the middle of the sprint.
|  |  |  | 3. Step Definition is in progress using Lambda Exp Style | [14 empty] | Cucumber Test Cases to be written. Facing NullPointerException for ETL Service. Changes pushed to ADO. Waiting for Manoj and Prashant review and feedback. More scenario need to added with VALID and INVALID GUID both testcase showing similar output behaviour.
'60% of development was completed #3,
Moved to Sprint#4
'This was assigned in the middle of the sprint.
Cucumber Test Cases to be written. Facing NullPointerException for ETL Service. Changes pushed to ADO. Waiting for Manoj and Prashant review and feedback. More scenario need to added with VALID and INVALID GUID both testcase showing similar output behaviour.
WPV | Jiban |  | AFA-11749 | Bank Account integration testing | PI#6 | 4 |  | 8 | 0 | 2020-12-22 | 2020-12-31 | 2021-01-13 | 2021-01-07 | 65% |  | Development | In Progress |  | 60% of development was completed #3, | PI#6-3 -- SPILL
|  |  |  | 1. Feature file is completed | [14 empty] | Moved to Sprint#4
|  |  |  | 2. Runner is completed | [14 empty] | 'This was assigned in the middle of the sprint.
|  |  |  | 3. Step Definition is in progress using Lambda Exp Style | [14 empty] | Cucumber Test Cases to be written. Facing NullPointerException for ETL Service. Changes pushed to ADO. Waiting for Manoj and Prashant review and feedback. More scenario need to added with VALID and INVALID GUID both testcase showing similar output behaviour.
'60% of development was completed #3,
Moved to Sprint#4
'This was assigned in the middle of the sprint.
Cucumber Test Cases to be written. Facing NullPointerException for ETL Service. Changes pushed to ADO. Waiting for Manoj and Prashant review and feedback. More scenario need to added with VALID and INVALID GUID both testcase showing similar output behaviour.
WPV | Pushkar |  | AFA-11551 | New Client Onboarding - PMDX Manager Enhancing hub configuration by adding Service definition tag | PI#6 | 4 |  | 8 | 8 | 2020-12-30 | 2020-12-31 | 2021-01-13 | 2021-01-13 | 100% |  | Closed | Completed |  | Completed : Source Code and Test Code Completed with 95% coverage. Fixed Code Smells as well. Updated PMDX Manager Runbook with latest Hub Command. | PI#6-4 -- NEW
|  |  |  | Completed | [14 empty] | PR raised on 6 Jan 2020. Prashant to do QA test for same starting 7 Jan. Prashant QA tested, attached inferences with test data commands on JIRA, PR merged to develop branch and marked this JIRA as closed on 7 Jan 2021.
- Add tag [Json array]
- Test cases [Expected array should match- runtime]File compared
- Service definition completed
WPV | Pushkar |  | AFA-11674 | Caching of list of Users fetched from listActiveUsers API by | PI#6 | 4 |  | 13 | 0 | 2020-12-16 | 2020-12-31 | 2021-01-13 | 2021-01-13 | 90% |  | Testing | In Progress |  | Need to leverage Caffeine Cache. Iterate through listActiveUsers and verify if IQID (User Proto) maps to eFrontInvestIQID (Aladdin User Object). Depends on AFA-11673. There are some dependencies on "Renata Roginsky" for IQID in API Response, once we get confirmation we can embrace that change as well into caching by IQID. Reneta is on leave till Jan first week. Himanshu moved the code to fetch list of Active Users to privatemarkets-transactions-common library. Currently, developing caching over same piece of code. API is not returning response. PR will be raised on 13 Jan. PR approved by Himanshu, Aditya and Rahul Mishra on 14 Jan. | PI#6-4 -- NEW
Aladidn Users Team in privatemarkets-common library
WPV | Shahul |  | AFA-11465 | Create Shell Share class - Managed fund /SPV | PI#6 | 4 |  | 8 | 8 | 2020-12-16 | 2020-12-31 | 2021-01-13 | 2021-01-06 | 100% |  | Closed | Completed |  | working on top of changes done by Aishwarya. Will raise PR on 29 Dec 2020. | PI#6-2 -- SPILL
|  |  |  | - Add new attribute in asset proto | [14 empty] | PR to be raised on 6 Jan. Need to move this story to Sprint 4. Environment dependency. Build was getting failed on 11 Jan.
- Call asset loader from portfolio transformer
- development
- Junit
- Cucumber testing [Need more information]
WPV | Shahul |  | AFA-11384 | Create FUND/PRIVATE Securities for Managed Funds and Managed Funds SPVs | PI#6 | 4 |  | 5 | 5 | 2020-12-16 | 2020-12-31 | 2021-01-13 | 2021-01-06 | 100% |  | Closed | Completed |  | working on top of changes done by Aishwarya. Will raise PR on 29 Dec 2020. | PI#6-3 -- SPILL
PR to be raised by 30th Dec. Need to move this story to Sprint 4. Environment dependency. Build was getting failed on 11 Jan.
WPV | Shahul |  | AFA-11746 | Adding Cucumber for Portfolio Plugin | PI#6 | 4 |  | 8 | 0 | 2020-12-21 | 2020-12-31 | 2021-01-13 | 2021-01-13 | 85% |  | Development | In Progress |  | Cucumber Test Cases to be written. 2 Test Cases running successfully. For 1 Test Case require new GUID. | PI#6-4 -- NEW
RC not yet found
WPV | Vivek |  | AFA-11379 | WPP-Txn : Bank Account Writer | PI#6 | 3 |  | 13 | 0 | 2020-12-16 | 2020-12-17 | 2021-12-30 | 2021-12-30 | 90% |  | Testing | In Progress |  | Dependency with Hub Configuration which is resolved now. | PI#6-3 -- NEW
Involved in code and API validation for same.
Dependency on code merge. Test Case 85% completed 15% pending. Postman testing in progress. Raised PR currently addressing review comments.PR approved and merged. Testing for flag related scenario is in progress. Evidence needs to be attached to JIRA. Review comments by Rahul Mishra fixed by Vivek. QA by Prashant in progress. One more round of testing in progress by Prashant.
WPV | Vivek |  | AFA-11379 | WPP-Txn : Bank Account Writer | PI#6 | 4 |  | 13 | 13 | 2020-12-16 | 2020-12-31 | 2021-01-13 | 2021-01-08 | 100% |  | Closed | Completed |  | Dependency with Hub Configuration which is resolved now. | PI#6-3 -- SPILL
Involved in code and API validation for same.
Dependency on code merge. Test Case 85% completed 15% pending. Postman testing in progress. Raised PR currently addressing review comments.PR approved and merged. Testing for flag related scenario is in progress. Evidence needs to be attached to JIRA. Review comments by Rahul Mishra fixed by Vivek. QA by Prashant in progress. One more round of testing in progress by Prashant.
WPV | Jiban |  | AFA-11749 | Bank Account integration testing | PI#6 | 5 |  | 8 | 0 | 2020-12-22 | 2021-01-14 | 2021-01-27 | 2021-01-19 | 85% |  | Code Review | In Progress |  | 60% of development was completed #5 | PI#6-3 -- SPILL
|  |  |  | 1. Feature file is completed | [14 empty] | * Received new API link.
|  |  |  | 2. Runner is completed | [14 empty] | * API with mulitple parameter
|  |  |  | 3. Step Definition is in progress using Lambda Exp Style | [14 empty] | Planning to raise PR 21 Jan.
Overall 85% Dev. Comp , Currently facing server issues (not booting). Once started , will raise PR for testing
WPV | Pushkar |  | AFA-11674 | Caching of list of Users fetched from listActiveUsers API by | PI#6 | 5 |  | 13 | 13 | 2020-12-16 | 2021-01-14 | 2021-01-27 | 2021-01-15 | 100% |  | Closed | Completed |  | PR approval delayed by 1 day | PI#6-4 -- SPILL
Aladidn Users Team in privatemarkets-common library
WPV | Pushkar |  | AFA-11767 | Cucumber for New Intraday User Mappings Gateway Calling Aladdin Graph Users API in aCRM workflow | PI#6 | 5 |  | 8 | 8 | 2021-01-13 | 2021-01-14 | 2021-01-27 | 2021-01-27 | 100% |  | Closed | Completed |  | Integrate with Aladdin Users API. Added Code to disable Caching for Users API for Recon and Non-Recon API call. Discussed with Rahul Verma and Alan Martinez if they have existing cucumber testcase for aCRMLoader. Also, contacted Harshita for E2E User API Testing from PMTC. PR raised on Friday. | PI#6-5 -- NEW
In Progress
* XYZ
Completed
* ABC
WPV | Shahul |  | AFA-11454 | Removing owner support in sec master | PI#6 | 5 |  | 5 | 5 | 2021-01-20 | 2021-01-14 | 2021-01-27 | 2021-01-27 | 100% |  | Closed | Completed |  | Analysis in progress. Raised PR on Friday. | PI#6-5 -- NEW
WPV | Shahul |  | AFA-11746 | Adding Cucumber for Portfolio Plugin | PI#6 | 5 |  | 8 | 8 | 2020-12-21 | 2021-01-14 | 2021-01-27 | 2021-01-27 | 100% |  | Closed | Completed |  | Cucumber Test Cases to be written. 2 Test Cases running successfully. For 1 Test Case require new GUID. | PI#6-4 -- SPILL
RC not yet found. PR raised will work on fixing review comments.
WPV | Vivek |  | AFA-11850 | Create JPA Entity and Related DAO Objects - Completed (Sub tasks) | PI#6 | 5 |  | 5 | 0 | 2020-12-20 | 2021-01-14 | 2021-01-27 | 2021-01-22 | 90% |  | Testing | In Progress |  | Dependency on Prashant Story . Development completed on Friday. | PI#6-5 -- NEW
|  |  |  | - Create Entity Classes | [14 empty] | PR Raised for QA but has dependency with Prashant Story - Protfolio Interface -Parent
- Create Dao Classes for Primary & Secondary Network
- Create Service Classes
WPV | Vivek |  | AFA-11903 | Writing Test cases for Performance JPA Entity, Dao classes and Service classes for Extern Delivery & Cantacts | PI#6 | 5 |  | 2 | 2 | 2021-01-27 | 2021-01-14 | 2021-01-27 | 2021-01-27 | 100% |  | Closed | Completed |  | Writing Test cases for Performance JPA Entity, Dao classes and Service classes for Extern Delivery & Cantacts | PI#6-5 -- NEW
WPV | Jiban |  | AFA-11749 | Bank Account integration testing | PI#6 | 6 |  | 8 | 8 | 2020-12-22 | 2021-01-28 | 2021-02-10 | 2021-02-10 | 100% |  | Closed | Completed |  | 60% of development was completed #5 | PI#6-3 -- SPILL
|  |  |  | 1. Feature file is completed | [14 empty] | * Received new API link.
|  |  |  | 2. Runner is completed | [14 empty] | * API with mulitple parameter
|  |  |  | 3. Step Definition is in progress using Lambda Exp Style | [14 empty] | Planning to raise PR 21 Jan.
Overall 85% Dev. Comp , Currently facing server issues (not booting). Once started , will raise PR for testing
WPV | Jiban |  | AFA-11904 | Cucumber Test : For Performance | PI#6 | 6 |  | 8 | 8 | 2021-01-28 | 2021-01-28 | 2021-02-10 | 2021-02-05 | 100% |  | Closed | Completed |  | need to call loadBatch api in transformer | PI#6-6 -- NEW
1. Feature file
2. Runner class
3. Step Definition file
4. util class for api calling
WPV | Pushkar |  | AFA-11947 | PMDX Manager Fixing Hub Config Issue : Empty entityTypes with Quotes | PI#6 | 6 |  | 1 | 1 | 2021-02-04 | 2021-01-28 | 2021-02-10 | 2021-02-05 | 100% |  | Closed | Completed |  | PR raised on 4 Feb and merged on 5 Feb. | PI#6-6 -- NEW
WPV | Pushkar |  | AFA-11905 | Cucumber : Asset Plugin in Transformer | PI#6 | 6 |  | 8 | 8 | 2021-01-28 | 2021-01-28 | 2021-02-10 | 2021-02-09 | 100% |  | Closed | Completed |  | Cucumber : Asset Plugin in Transformer | PI#6-6 -- NEW
|  |  |  | 1. StepDefinition | [14 empty] | 1. StepDefinition
|  |  |  | 2. Feature (Positive and Negative Scenario) | [14 empty] | 2. Feature (Positive and Negative Scenario)
Prashant to provide Asset GUID for negative scenario.
PR raised and merged on 8 Feb 2020
WPV | Shahul |  | AFA-11454 | Removing owner support in sec master | PI#6 | 6 |  | 5 | 5 | 2021-01-20 | 2021-01-14 | 2021-01-27 | 2021-01-27 | 100% |  | Closed | Completed |  | Analysis in progress. Raised PR on Friday. | PI#6-5 -- SPILL
WPV | Shahul |  | AFA-11808 | Disable Funtionality that calculates local FX net_nav | PI#6 | 6 |  | 5 | 5 | 2021-01-28 | 2021-01-28 | 2021-02-10 | 2021-02-05 | 100% |  | Closed | Completed |  | Proto PR merged | PI#6-6 -- NEW
WPV | Shahul |  | AFA-11882 | Load all decodes at the startup of transformer | PI#6 | 6 |  | 3 | 3 | 2021-01-28 | 2021-01-28 | 2021-02-10 | 2021-02-02 | 100% |  | Closed | Completed |  | PR merged. | PI#6-6 -- NEW
WPV | Vivek |  | AFA-11850 | Create JPA Entity and Related DAO Objects - Completed (Sub tasks) | PI#6 | 6 |  | 5 | 5 | 2020-12-20 | 2021-01-28 | 2021-02-10 | 2021-02-10 | 100% |  | Closed | Completed |  | Dependency on Prashant Story . Development completed on Friday. | PI#6-5 -- SPILL
|  |  |  | - Create Entity Classes | [14 empty] | PR Raised for QA but has dependency with Prashant Story - Protfolio Interface -Parent
- Create Dao Classes for Primary & Secondary Network
- Create Service Classes
WPV | Vivek |  | AFA-11902 | Writing Test cases for Performance WPP-Txn: Link eFront Bank Account to Portfolio | PI#6 | 6 |  | 2 | 2 | 2021-01-27 | 2021-01-28 | 2021-02-10 | 2021-02-10 | 100% |  | Closed | Completed |  | Writing Test cases for Performance WPP-Txn: Link eFront Bank Account to Portfolio | PI#6-5 -- NEW
WPV | Vivek |  | AFA-11762 | Build Improvement. Build is taking long time. This is mostly due to external DB connection. We must identify and mock these test cases. | PI#6 | 6 |  | 8 | 8 | 2021-01-28 | 2021-01-28 | 2021-02-10 | 2021-02-08 | 100% |  | Closed | Completed |  | ADO performance issue , this task is to analyis to reduce time. Analyzing Loader and Hub test Classes. PR raised on 4 Feb with CRMLoader Changes. CRM Team approval is pending. | PI#6-6 -- NEW
WPV | Jiban |  | AFA-11974 | Add withHolding Fees to PMTC cucumber test | PI#6 | 7 |  | 3 | 0 | 2021-02-10 | 2021-02-11 | 2021-02-24 | 2021-02-24 | 10% |  | Development | In Progress |  | Add withHolding Fees to PMTC cucumber test | PI#6-7 -- NEW
WPV | Pushkar |  | AFA-12000 | Cucumber : Instruments in Transformer | PI#6 | 7 |  | 8 | 8 | 2021-02-10 | 2021-02-11 | 2021-02-24 | 2021-02-23 | 100% |  | Closed | Completed |  | PR raised on 18 Feb and merged on 22 Feb. | PI#6-7 -- NEW
1. StepDefinition
2. Feature (Positive and Negative Scenario)
WPV | Shahul |  | AFA-11949 | Allow negative port codes in PMDX | PI#6 | 7 |  | 5 | 5 | 2021-02-10 | 2021-02-11 | 2021-02-24 | 2021-02-19 | 100% |  | Closed | Completed |  | Faced issue with CashResponse related classes. got resolved it on the end of 16th Feb. | PI#6-7 -- NEW
WPV | Vivek |  | AFA-12012 | Add Cucumber Test For Asset Loader | PI#6 | 7 |  | 5 | 5 | 2021-02-11 | 2021-02-11 | 2021-02-24 | 2021-02-23 | 100% |  | Closed | Completed |  | Cucumber : Asset Loader Create and Update Asset Done | PI#6-7 -- NEW
Scenario Covered:-
Create/Update for Asset
Create/Update for Instrument
Create/Update for Performance
WPV | Jiban |  | AFA-11974 | Add withHolding Fees to PMTC cucumber test | PI#6 | 8 |  | 3 | 3 | 2021-02-10 | 2021-02-25 | 2021-03-10 | 2021-03-10 | 100% |  | Closed | Completed |  | Add withHolding Fees to PMTC cucumber test | PI#6-7 -- SPILL
WPV | Jiban |  | AFA-11966/187171 | Cucumber : PMTC Bank Operations | PI#6 | 8 |  | 8 | 8 | 2021-02-25 | 2021-02-25 | 2021-03-10 | 2021-03-10 | 100% |  | Closed | Completed |  | Cucumber : PMTC Bank Operations. PMTC calling TPS bug found in TPS. Check with Rahul M. | PI#6-8 -- NEW
WPV | Pushkar |  | AFA-11764/187183 | Log Clean Up for Transformer | PI#6 | 8 |  | 5 | 5 | 2021-02-24 | 2021-02-25 | 2021-03-10 | 2021-03-10 | 100% |  | Closed | Completed |  | Meaningful Exceptions, Before and After Transformation, Avoid NPE and RTE, Handle Exceptions Gracefully. PR raised on 5 March 2020. Fixed review comments.Require 2 approval to close this JIRA. | PI#6-8 -- NEW
WPV | Shahul |  | AFA-11412/187175 | PMDX processing vs non processing Data Configuration | PI#6 | 8 |  | 5 | 0 | 2021-03-01 | 2021-02-25 | 2021-03-10 | 2021-03-10 | 90% |  | Development | In Progress |  | Code pushed to feature branch. facing build issues. once fixed, will raise PR | PI#6-8 -- NEW
WPV | Vivek |  | AFA-12012 | Add Cucumber Test case for Asset Loader - PARENT JIRA | PI#6 | 8 |  | 5 | 5 | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-10 | 100% |  | Closed | Completed |  | Cucumber : Asset Loader Create and Update Asset in Progress. Asset, Performance and Instruments. This US will be split. As per Aishwarya, this US will get split to cover all scenarios. | PI#6-8 -- NEW
WPV | Vivek |  | AFA-12085/187180 | Add Cusip to Asset Reader logs & allow AssetName to be printed | PI#6 | 8 |  | 3 | 3 | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-10 | 100% |  | Closed | Completed |  | Add Cusip to Asset Reader logs & allow AssetName to be printed | PI#6-8 -- NEW
WPV | Jiban |  | AFA-11975/187694 | Create Cucumber test for update ADL | PI#7 | 0 |  | 5 | 5 | 2021-03-15 | 2021-03-11 | 2021-03-24 | 2021-03-24 | 100% |  | Closed | Completed |  | Create Cucumber test for update ADL | PI#7-0 -- NEW
WPV | Pushkar |  | 187603 | Cucumber : Fundamentals Reader and Writer | PI#7 | 0 |  | 8 | 8 | 2021-03-15 | 2021-03-11 | 2021-03-24 | 2021-03-24 | 100% |  | Closed | Completed |  | Cucumber : Fundamentals Reader and Writer. FR and FW app servers working. Code skeleton completed. Currently capturing scenarios. | PI#7-0 -- NEW
WPV | Shahul |  | AFA-11412/187175 | PMDX processing vs non processing Data Configuration | PI#7 | 0 |  | 5 | 0 | 2021-03-01 | 2021-03-11 | 2021-03-24 | 2021-03-10 | 90% |  | Testing | In Progress |  | Code pushed to feature branch. facing build issues. once fixed, will raise PR. Moved from PI 6 Sprint 8 to PI 7 Sprint 0 | PI#6-8 -- SPILL
WPV | Vivek |  | 187078 | Cucumber Test Case - Asset | PI#7 | 0 |  | 5 | 5 | 2021-03-08 | 2021-03-11 | 2021-03-24 | 2021-03-12 | 100% |  | Closed | Completed |  | Cucumber : Asset Loader Create and Update Asset in Progress. Asset, Performance and Instruments. This US will be split. As per Aishwarya, this US will get split to cover all scenarios. | PI#7-0 -- NEW
WPV | Jiban |  | 374616 | Fix Failing secondary pipeline in ADO | PI#7 | 1 |  | 5 | 0 | 2021-03-25 | 2021-03-25 | 2021-04-07 | 2021-04-06 | 50% |  | Active | In Progress | Last | Fix Failing secondary pipeline in ADO | PI#7-1 -- NEW
WPV | Jiban |  | 380295 | Add support for historical transaction in pmdx hub | PI#7 | 1 |  | 5 | 0 | 2021-04-01 | 2021-03-25 | 2021-04-07 | 2021-04-06 | 90% |  | Active | In Progress | Last | in Testing | PI#7-1 -- NEW
WPV | Pushkar |  | 374435 | Fix the secondary pipeline build for cucumber to help quantify coverage | PI#7 | 1 |  | 8 | 8 | 2021-03-24 | 2021-03-25 | 2021-04-07 | 2021-04-06 | 100% |  | Closed | Completed | Last | Fix the secondary pipeline build for cucumber to help quantify coverage | PI#7-1 -- NEW
WPV | Shahul |  | AFA-11412/187175 | PMDX processing vs non processing Data Configuration | PI#7 | 1 |  | 5 | 0 | 2021-03-01 | 2021-03-25 | 2021-04-07 | 2021-04-07 | 90% |  | Testing | In Progress | Last | Code pushed to feature branch. facing build issues. once fixed, will raise PR. Moved from PI 6 Sprint 8 to PI 7 Sprint 0 | PI#6-8 -- SPILL
WPV | Shahul |  | 165264 | PMAR Filtering for Private Markets Support | PI#7 | 1 |  | 5 | 0 | 2021-03-25 | 2021-03-25 | 2021-04-07 | 2021-04-07 | 60% |  | Testing | In Progress | Last | PMAR Filtering for Private Markets Support | PI#7-1 -- NEW
WPV | Vivek |  | 187068 | Cucumber Test Case - Instrument | PI#7 | 1 |  | 5 | 5 | 2021-03-08 | 2021-03-11 | 2021-03-24 | 2021-03-12 | 100% |  | Closed | Completed | Last | Cucumber Test Case - Instrument. PR raised. | PI#7-1 -- NEW
WPV | Vivek |  | 187076 | Cucumber Test Case - Performance | PI#7 | 1 |  | 5 | 5 | 2021-03-24 | 2021-03-25 | 2021-04-07 | 2021-04-06 | 100% |  | Closed | Completed | Last | Cucumber Test Case - Performance. PR raised. | PI#7-1 -- NEW
WPV | Jiban |  | 374616 | Fix Failing secondary pipeline in ADO | PI#7 | 2 |  | 5 | 0 | 2021-03-25 | 2021-04-08 | 2021-04-21 | 2021-04-21 | 60% |  | Active | In Progress | Current | Fix Failing secondary pipeline in ADO | PI#7-1 -- SPILL
WPV | Jiban |  | 380295 | Add support for historical transaction in pmdx hub | PI#7 | 2 |  | 5 | 5 | 2021-04-01 | 2021-04-08 | 2021-04-21 | 2021-04-21 | 100% |  | Closed | Completed | Current | in Testing | PI#7-1 -- SPILL
WPV | Jiban |  | 374602 | Cucumber Test Case - Naked Bank Ops | PI#7 | 2 |  | 5 | 5 | 2021-04-08 | 2021-04-08 | 2021-04-21 | 2021-04-21 | 90% |  | Closed | Completed | Current | Fix Failing secondary pipeline in ADO | PI#7-2 -- NEW
WPV | Pushkar |  | AFA-12084/187600 | Add logs for Fundamentals Reader | PI#7 | 2 |  | 5 | 5 | 2021-04-08 | 2021-04-08 | 2021-04-21 | 2021-04-21 | 100% |  | Closed | Completed | Current | Add logs for Fundamentals Reader | PI#7-2 -- NEW
WPV | Pushkar |  | 187111 | Add logs for Fundamentals Writer | PI#7 | 2 |  | 5 | 5 | 2021-04-08 | 2021-04-08 | 2021-04-21 | 2021-04-21 | 100% |  | Closed | Completed | Current | Add logs for Fundamentals Writer | PI#7-2 -- NEW
WPV | Shahul |  | AFA-11412/187175 | PMDX processing vs non processing Data Configuration | PI#7 | 2 |  | 5 | 5 | 2021-03-01 | 2021-04-08 | 2021-04-21 | 2021-04-21 | 100% |  | Closed | Completed | Current | Code pushed to feature branch. facing build issues. once fixed, will raise PR. Moved from PI 6 Sprint 8 to PI 7 Sprint 0 | PI#6-8 -- SPILL
WPV | Shahul |  | 165264 | PMAR Filtering for Private Markets Support | PI#7 | 2 |  | 5 | 5 | 2021-03-25 | 2021-04-08 | 2021-04-21 | 2021-04-21 | 100% |  | Closed | Completed | Current | PMAR Filtering for Private Markets Support | PI#7-1 -- SPILL
WPV | Shahul |  | 400727 | Share Class : Test Portfolio Group API | PI#7 | 2 |  | 2 | 2 | 2021-04-15 | 2021-04-08 | 2021-04-21 | 2021-04-21 | 100% |  | Closed | Completed | Current | Share Class : Test Portfolio Group API | PI#7-2 -- NEW
WPV | Vivek |  | 389694 | Cucumber Test Case - Asset Loader - Asset Reader | PI#7 | 2 |  | 5 | 5 | 2021-04-08 | 2021-04-08 | 2021-04-21 | 2021-04-21 | 100% |  | Closed | Completed | Current | Cucumber Test Case - Asset Loader - Asset Reader | PI#7-2 -- NEW
WPV | Pushkar |  | 398433 | Cucumber : Investor Broker Creation | PI#7 | 3 |  | 8 | 0 | 2021-04-22 | 2021-04-22 | 2021-05-05 | 2021-05-05 | 0% |  | New | New |  | Cucumber : Investor Broker Creation | PI#7-3 -- NEW